## FDPjune-final
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE SECOND QUARTER, CY 2015
Province, City or Municipality: NEGROS ORIENTAL
|  |  |  | Target | Project Status |  | No. of
|  |  |  | Completion | % of | Total Cost | Extensions
Program or Project | Location | Total Cost | Date Started | Date | Completion | Incurred to Date | if any | Remarks
SOCIAL DEVELOPMENT
RES#861-CONSTRUCTION OF MULTI-PURPOSE BUILDING/EVACUATION CENTER,BARANGAY MASULOG, CANLAON CITY | Canlaon City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-ADD'L. APPROPRIATION FOR THE CONST. OF MULTI-PURPOSE BUILDING/EVACUATION CENTER,BARANGAY HILAITAN,GUIHULNGAN CITY | Guihulngan City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE BUILDING/EVACUATION CENTER,BARANGAY MAGSAYSAY,GUIHULNGAN CITY | Guihulngan City, Negros Oriental | 500000 |  |  |  | 0
RES#861-COMPLETION OF THE CONSTRUCTION OF MULTI-PURPOSE HALL, BARANGAY CAMBAYE, TAYASAN | Tayasan, Negros Oriental | 200000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE BUILDING/EVACUATION CENTER,BARANGAY JANDALAMANON, AYUNGON | Ayungon, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE BUILDING/EVACUATION CENTER,BRGY AWAAN,AYUNGON | Ayungon, Negros Oriental | 400000 |  |  |  | 0
RES#861-LOOC PORT DEVELOPMENT PROJECT, TAMPOCON I, AYUNGON(PHASE II) | Ayungon, Negros Oriental | 1000000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE HALL & EVACUATION CENTER, POBLACION, AYUNGON | Ayungon, Negros Oriental | 1000000 |  |  |  | 0
RES#861-ADD'L. APPROP.FOR THE CONSTRUCTION OF MULTI-PURPOSE BUILDING, BARANGAY POBLACION, MANJUYOD | Manjuyod, Negros Oriental | 3000000 |  |  |  | 0
RES#861-ADD'L. APPROP. FOR THE CONSTRUCTION OF MULTI-PURPOSE/EVACUATION CENTER,POBLACION,BINDOY | Bindoy, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE BUILDING/EVACUATION CENTER, BARANGAY I, BAIS CITY | Bais City, Negros Oriental | 2000000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE BUILDING/EVACUATION CENTER,BRGY LONOY,BAIS CITY | Bais City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE BUILDING, BARANGAY BULWANG, MABINAY | Mabinay, Negros Oriental | 1000000 |  |  |  | 0
RES#861-CONSTRUCTION OF BADC MULTI-PURPOSE BUILDING, BARANGAY MANLINGAY, MABINAY | Mabinay, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE BUILDING/EVACUATION CENTER, TADLONG, MABINAY | Mabinay, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE BLDG/EVACUATION CENTER,BRGY LUMBANGAN,MABINAY | Mabinay, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE BLDG/EVACUATION CENTER,BRGY INAPOY,MABINAY | Mabinay, Negros Oriental | 1000000 |  |  |  | 0
RES#861-ADD'L. APPROPRIATION FOR THE CONSTRUCTION OF MULTI-PURPOSE BUILDING, BARANGAY 9, TANJAY CITY | Tanjay City, Negros Oriental | 500000 |  |  |  | 0
RES#861-ADD'L. APPROPRIATION FOR THE CONSTRUCTION OF MULTI-PURPOSE BUILDING/EVACUATION CENTER, AZAGRA, TANJAY CITY | Tanjay City, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE BLDG/EVACUATION CENTER,BRGY CALICANAN,PAMPLONA | Pamplona, Negros Oriental | 1000000 |  |  |  | 0
RES#861-ADD'L. FUNDING FOR THE CONSTRUCTION OF MULTI-PURPOSE BUILDING/EVACUATION CENTER AT BARANGAY POBLACION, AMLAN | Amlan, Negros Oriental | 1800000 |  |  |  | 0
RES#861-ADD'L.FUNDING FOR THE IMPROVEMENT OF EXISTING MULTI-PURPOSE CENTER @ BRGY POBLACION, AMLAN | Amlan, Negros Oriental | 819465 |  |  |  | 0
RES#861-CONSTRUCTION OF EVACUATION CENTER, TANDAYAG, AMLAN | Amlan, Negros Oriental | 1000000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE BLDG/EVACUATION CENTER,BRGY POBLACION,SIBULAN | Sibulan, Negros Oriental | 1300000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT OF MULTI-PURPOSE BLDG AT BRGY PULANGTUBIG,DUMAGUETE CITY | Dumaguete City, Negros Oriental | 800000 |  |  |  | 0
RES#861-CONSTRUCTION OF TWO STOREY MULTI-PURPOSE BUILDING, BARANGAY BALUGO, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-CONSTRUCTION OF EVACUATION CENTER/MPP AT TACLOBO HS, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE BUILDING, SAGBANG, VALENCIA | Valencia, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE HALL/EVACUATION CENTER, BRGY SAN MIGUEL,BACONG | Bacong, Negros Oriental | 1000000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE BUILDING/EVACUATION CENTER, BAGACAY, DAUIN | Dauin, Negros Oriental | 1000000 |  |  |  | 0
RES#861-IMPROVEMENT/REHABILITATION OF MULTI-PURPOSE HALL, BARANGAY MAG-ASO, DAUIN | Dauin, Negros Oriental | 600000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE BUILDING/EVACUATION CENTER,BRGY SANDULOT,SIATON | Siaton, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE BUILDING/EVACUATION CENTER AT BRGY GILIGAON,SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE BUILDING/EVACUATION CENTER,BRGY TAYAK,SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-REPAIR OF MULTI-PURPOSE HALL/EVACUATION CENTER, BARANGAY INALAD, SIATON | Siaton, Negros Oriental | 250000 |  |  |  | 0
RES#861-REHABILITATION OF MULTI-PURPOSE HALL/EVACUATION CENTER, BARANGAY 3, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-COMPLETION OF MULTI-PURPOSE BLDG/EVACUATION CENTER,BRGY II,POBLACION,SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE BUILDING, BARANGAY MILAGROSA, STA. CATALINA | Sta. Catalina, Negros Oriental | 500000 |  |  |  | 0
RES#861-ADD'L. APPROPRIATION FOR THE CONST. OF MULTI-PURPOSE BUILDING/EVACUATION CENTER, KALUMBOYAN, BAYAWAN CITY | Bayawan City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-CONSTRUCTION OF BARANGAY TINAGO MULTI-PURPOSE HALL(BACKFILLING ONLY)BAYAWAN CITY | Bayawan City, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF POBLACION EVACUATION CENTER, POBLACION, BASAY | Basay, Negros Oriental | 1000000 |  |  |  | 0
RES#861-COMPLETION OF PUBLIC MARKET, POBLACION, MANJUYOD | Manjuyod, Negros Oriental | 300000 |  |  |  | 0
RES#861-ADDITIONAL APPROPRIATION FOR THE CONSTRUCTION OF PUBLIC MARKET, STA. CATALINA | Sta. Catalina, Negros Oriental | 3000000 |  |  |  | 0
RES#861-CONSTRUCTION/INSTALLATION OF TENTS TO SERVE AS EVACUATION CENTER DURING CALAMITIES IN BRGY. POBLACION,STA.CATALINA | Sta. Catalina, Negros Oriental | 550000 |  |  |  | 0
RES#861-CONST/INST. OF TENTS TO SERVE AS EVACUATION CENTER DURING CALAMITY @10,000 EACH BRGYS:2-VALENCIA,18-BACONG,6-ZAMBOANGUITA,3-DAUIN,3-BASAY,13-SIATON,11-STA.CATALINA,10-BAYAWAN CITY, IN THE 3RD DISTRICT |  | 670000 |  |  |  | 0
RES#861-ADD'L BUDGET TO THE 1.5MILLION CY 2014 ALLOCATION FOR THE CONSTRUCTION OF EVACUATION CENTER AT BRGY.TINAOGAN,BINDOY | Bindoy, Negros Oriental | 1500000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE BUILDING, POBLACION, GUIHULNGAN CITY | Guihulngan City, Negros Oriental | 100000 |  |  |  | 0
RES#861-IMPROVEMENT/REHAB OF MULTI-PURPOSE HALL IN BRGY. MANDUAO, BAYAWAN CITY | Bayawan City, Negros Oriental | 50000 |  |  |  | 0
RES#861-CONSTRUCTION/REHAB OF MULTI-PURPOSE HALL IN BRGY. TINAGO, BAYAWAN CITY | Bayawan City, Negros Oriental | 50000 |  |  |  | 0
RES#861-IMPROVEMENT/REHAB. OF MULTI-PURPOSE HALL IN BRGY. SUBA, BAYAWAN CITY | Bayawan City, Negros Oriental | 50000 |  |  |  | 0
RES#861-CONSTRUCTION/REHAB OF MULTI-PURPOSE HALL IN BRGY. BALAYAGMANOK, VALENCIA | Valencia, Negros Oriental | 100000 |  |  |  | 0
RES#861-CNSTRUCTION/REHAB. OF MULTI-PURPOSE HALL IN BRGY. CALAYUGAN, VALENCIA | Valencia, Negros Oriental | 100000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE BUILDING IN BRGY. BANBAN, AYUNGON | Ayungon, Negros Oriental | 50000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE HALL IN BRGY. BULOD, BINDOY | Bindoy, Negros Oriental | 20000 |  |  |  | 0
RES#861-IMPROVEMENT OF AYUNGON PUBLIC MARKET, AYUNGON | Ayungon, Negros Oriental | 130000 |  |  |  | 0
RES#861-CONSTRUCTION OF BAGSAKAN CENTER,JIMALALUD | Jimalalud,NegOr | 150000 |  |  |  | 0
RES#861-CONSTRUCTION/REHABILITATION/IMPROVEMENT OF JUGNO, AMLAN MULTI PURPOSE HALL | Amlan, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT/REHAB OF MULTI-PURPOSE HALL FOR BRGY.DOBDOB,VALENCIA HIGH SCHOOL | Valencia, Negros Oriental | 100000 |  |  |  | 0
RES#861-PURCHASE OF CALAMITY-RELATED RESCUE EQUIPMENT(REPEATER) W/IN 2ND DISTRICT |  | 100000 |  |  |  | 0
RES#861-PURCHASE OF CALAMITY-RELATED RESCUE EQUIPMENT(BASE RADIOS)FOR ALL THE CITIES & MUNICIPALITIES IN THE 2ND DISTRICT |  | 68000 |  |  |  | 0
RES#861-PURCHASE OF CALAMITY-RELATED RESCUE EQUIPMENT(TWO-WAY HANDHELD RADIOS)FOR THE FF:8BRGYS-AMLAN,6BRGYS-BAIS,24BRGYS-TANJAY,15BRGYS-SIBULAN;16-PAMPLONA,14-SAN JOSE,30-DGTE. CITY |  | 1026000 |  |  |  | 0
RES#861-PURCHASE OF CALAMITY-RELATED RESCUE EQUIPMENT(GENERATOR)FOR THE FF:10BRGYS-BAIS,14BRGYS-TANJAY,8BRGYS-SIBULAN,14BRGYS-SAN JOSE |  | 306000 |  |  |  | 0
RES#861-PURCHASE OF APPROPRIATE CALAMITY-RELATED RESCUE OPERATIONS EQUIPMENT:CHAINSAWS & TWO-WAY HANDHELD RADIOS TO ALL MUNICIPALITIES & CITIES IN THE 2ND DISTRICT |  | 1000000 |  |  |  | 0
RES#861-PURCHASE OF CALAMITY-RELATED RESCUE EQUIPMENT(TWO-WAY HANDHELD RADIOS)FOR 165 BARANGAYS IN THE 3RD DISTRICT |  | 1500000 |  |  |  | 0
RES#861-PUR. OF CALAMITY-RELATED RESCUE EQUIPMENT(MOBILE GENERATOR) @10,000 EACH BRGYS:2-VALENCIA,18-BACONG,6-ZAMBOANGUITA,3-DAUIN,3-BASAY,13-SIATON,11-STA.CATALINA,10-BAYAWAN CITY, IN THE 3RD DISTRICT |  | 670000 |  |  |  | 0
RES#861-PURCHASE OF CALAMITY-RELATED RESCUE EQUIPMENT(TWO-WAY HANDHELD RADIO) FOR ALL BARANGAYS IN THE PROVINCE |  | 1500000 |  |  |  | 0
RES#861-PURCHASE OF CALAMITY-RALATED RESCUE OPERATIONS EQUIPMENT(TRANSISTOR MEGAPHONE)FOR ALL CITIES & MUNICIPALITIES |  | 250000 |  |  |  | 0
RES#861-PURCHASE OF TWO-WAY HAND-HELD RADIO FOR BRGYS POBLACION,HILAITAN,BULADO,MCKINLEY,GUIHULNGAN;BRGY POBLACION,TAYASAN,MUN. OF AYUNGON,VALLEHERMOSO,MANJUYOD&CANLAON CITY |  | 100000 |  |  |  | 0
PURCHASE OF GENERATOR SET FOR GUIHULNGAN CITY | Guihulngan City | 50000 |  |  |  | 0
RES#861-PURCHASE OF CALAMITY RELATED EQUIPMENT(GENERATOR)FOR THE FF BRGYS:27-MANJUYOD,22-BINDOY,24-AYUNGON,28-TAYASAN,28-JIMALALUD,29-LA LIBERTAD,33-GUIHULNGAN,15-VALLEHERMOSO,12-CANLAON |  | 1500000 |  |  |  | 0
RES#861-PURCHASE OF REHABILITATION & FITNESS EQUIPMENT FOR CANLAON CITY | Canlaon City, Negros Oriental | 100000 |  |  |  | 0
RES#861-PURCHASE OF CALAMITY RELATED RESCUE OPERATION EQUIPMENT(75UGEN,23UCHAINSAW,66U HHRADIO DIFF BRGYS 2ND DIST) |  | 1500000 |  |  |  | 0
RES#861-REFURBISHMENT OF SOCIAL HYGEINE CLINIC, CANLAON CITY | Canlaon City, Negros Oriental | 100000 |  |  |  | 0
RES#861-COMPLETION OF BARANGAY HEALTH STATION, MAHANLUD, JIMALALUD | Jimalalud, Negros Oriental | 200000 |  |  |  | 0
RES#861-IMPROVEMENT OF BARANGAY HEALTH STATION, SAYING, TAYASAN | Tayasan, Negros Oriental | 400000 |  |  |  | 0
RES#861-ADDITIONAL FUNDS FOR THE CONSTRUCTION OF MATOBATO BARANGAY HEALTH STATION, BINDOY | Bindoy, Negros Oriental | 200000 |  |  |  | 0
RES#861-CONSTRUCTION OF THE BAIS CITY HEALTH CENTER FACILITY, BAIS CITY | Bais City, Negros Oriental | 3072680 |  |  |  | 0
RES#861-CONSTRUCTION OF BARANGAY HEALTH CENTER, BARANGAY NEW NAMANGKA,MABINAY | Mabinay, Negros Oriental | 400000 |  |  |  | 0
RES#861-COMPLETION OF HEALTH CENTER, BARANGAY 7, TANJAY CITY | Tanjay City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-REFURBISHMENT OF SOCIAL HYGIENE CLINIC AT TANJAY CITY HEALTH OFFICE,TANJAY CITY | Tanjay City, Negros Oriental | 100000 |  |  |  | 0
RES#861-IMPROVEMENT OF BARANGAY HEALTH STATION, BARANGAY APO, DAUIN | Dauin, Negros Oriental | 200000 |  |  |  | 0
RES#861-IMPROVEMENT OF NABILOG COMMUNITY PRIMARY HOSPITAL, TAYASAN | Tayasan, Negros Oriental | 100000 |  |  |  | 0
RES#861-IMPROVEMENT OF X-RAY ROOM FOR MABINAY MCH, MABINAY | Mabinay, Negros Oriental | 235450 |  |  |  | 0
RES#861-IMPROVEMENT OF LYING-IN CLINIC IN BRGY. TAGBINO, VALLEHERMOSO | Vallehermoso, Negros Oriental | 100000 |  |  |  | 0
RES#861-REHABILITATION OF HEALTH CENTERS FOR BRGY TAMAO, JIMALALUD | Jimalalud, Negros Oriental | 200000 |  |  |  | 0
RES#861-REHABILITATION OF HEALTH CENTER FOR BARANGAY CANGHARAY, JIMALALUD | Jimalalud, Negros Oriental | 200000 |  |  |  | 0
RES#861-REPAIR & IMPROVEMENT OF MAASLUM, AYUNGON HEALTH CENTER | Ayungon, Negros Oriental | 150000 |  |  |  | 0
RES#861-PURCHASE OF MEDICAL EQUIPMENTS FOR MABATO, AYUNGON HEALTH CENTER | Ayungon, Negros Oriental | 100000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT/REHABILITATION/ OF SANDULOT BALANAN, SIATON HEALTH CENTER | Siaton, Negros Oriental | 150000 |  |  |  | 0
RES#861-PURCHASE OF MEDICAL EQUIPMENT FOR CANLAON DISTRICT HOSPITAL, CANLAON CITY | Canlaon City, Negros Oriental | 192000 |  |  |  | 0
RES#861-PURCHASE OF AMBULANCE FOR THE USE OF PACUAN COMMUNITY PRIMARY HOSPITAL, LA LIBERTAD | La Libertad, Negros Oriental | 1800000 |  |  |  | 0
RES#861-PURCHASE OF MEDICAL EQUIPMENT, POBLACION RHU, BASAY | Basay, Negros Oriental | 200000 |  |  |  | 0
RES#861-PURCHASE OF MEDICAL EQUIPMENT FOR THE LYING-IN-CLINIC IN THE RURAL HEALTH UNIT, MANJUYOD | Manjuyod, Negros Oriental | 100000 |  |  |  | 0
RES#861-PURCHASE OF MEDICAL EQUIPMENT(NEBULIZER & BLOOD PRESSURE APPARATUS)FOR ALL CITIES & MUNICIPALITIES |  | 850000 |  |  |  | 0
RES#861-PURCHASE OF MEDICAL EQUIPMENT INTENDED FOR BARANGAY HEALTH CENTER OF BRGY. CANLARGO,BAIS CITY | Bais City, Negros Oriental | 40000 |  |  |  | 0
RES#861-PURCHASE OF MEDICAL EQUIPMENT FOR THE MUN. OF VALLEHERMOSO,TAYASAN,AYUNGON,MANJUYOD & JIMALALUD |  | 300000 |  |  |  | 0
RES#861-STREET LIGHTING FROM EXODUS AVENUE TERMINAL DOWN TO BRGY BINALBAGAN,BRGY PANUBIGAN,CANLAON CITY | Canlaon City, Negros Oriental | 400000 |  |  |  | 0
RES#861-INSTALLATION/MAINTENANCE OF STREET LIGHTS, SO. TIBABAY-AN, BRGY LUCAY, MANJUYOD | Manjuyod, Negros Oriental | 300000 |  |  |  | 0
RES#861-INSTALLATION/MAINTENANCE OF STREET LIGHTS, SO. JAMLON, BRGY LAMOGONG, MANJUYOD | Manjuyod, Negros Oriental | 200000 |  |  |  | 0
RES#861-INSTALLATION & MAINTENANCE OF STREET LIGHTING SYSTEM IN BRGY. BONGALONAN, BASAY | Basay, Negros Oriental | 50000 |  |  |  | 0
RES#861-INSTALLATION & MAINTENANCE OF STREET LIGHTING SYSTEM IN BRGY. ACTIN, BASAY | Basay, Negros Oriental | 50000 |  |  |  | 0
RES#861-INSTALLATION & MAINTENANCE OF STREET LIGHTING SYSTEM IN BRGY. LINANTAYAN, BASAY | Basay, Negros Oriental | 50000 |  |  |  | 0
RES#861-INSTALLATION & MAINTENANCE OF STREET LIGHTING SYSTEM IN BRGY. TABUAN, BAYAWAN CITY | Bayawan City, Negros Oriental | 50000 |  |  |  | 0
RES#861-INSTALLATION & MAINTENANCE OF STREET LIGHTING SYSTEM IN BRGY BANAY-BANAY, BAYAWAN | Bayawan City, Negros Oriental | 50000 |  |  |  | 0
RES#861-INSTALLATION/MAINTENANCE OF STREET LIGHTING SYSTEM , BRGY. BONG-BONG, VALENCIA | Valencia, Negros Oriental | 20000 |  |  |  | 0
RES#861-INSTALLATION/MAINTENANCE OF STREET LIGHTING SYSTEM, BRGY. WEST BALABAG, VALENCIA | Valencia, Negros Oriental | 20000 |  |  |  | 0
RES#861-INSTALLATION & MAINTENANCE OF STREET LIGHTING SYSTEM IN GUIHULNGAN, JIMALALUD, VALLEHERMOSO & MANJUYOD |  | 100000 |  |  |  | 0
RES#861-INSTALLATION & MAINTENANCE OF STREET LIGHTING SYSTEM OF BRGY NAGBOALAO, BASAY | Basay, Negros Oriental | 100000 |  |  |  | 0
RES#861-IMPROVEMENT OF OYSTER FARM FACILITIES, BARANGAY CAPIÑAHAN, BAIS CITY | Bais City, Negros Oriental | 600000 |  |  |  | 0
RES#861-IMPROVEMENT OF DRAINAGE SYSTEM IN FRONT OF ROMAN CATHOLIC CHURCH, POBLACION,TAYASAN | Tayasan, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION OF DRAINAGE CANAL AT ZULUETA STREET, MANJUYOD | Manjuyod, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF DRAINAGE SYSTEM, BARANGAY TUPAS, MANJUYOD | Manjuyod, Negros Oriental | 505778 |  |  |  | 0
RES#861-IMPROVEMENT OF DRAINAGE CANAL, BARANGAY OBOGON, TANJAY CITY | Tanjay City, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF DRAINAGE CANAL, SO. ASIOTES, BARANGAY POLO, TANJAY CITY | Tanjay City, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF DRAINAGE CANAL, BARANGAY 5, POBLACION, TANJAY CITY | Tanjay City, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF DRAINAGE SYSTEM ALONG TINAGO ROAD, BARANGAY POBLACION, AMLAN | Amlan, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF DRAINAGE SYSTEM, BARANGAY STO. NIÑO, SAN JOSE | San Jose, Negros Oriental | 200000 |  |  |  | 0
RES#861-CONST. OF LINE CANAL DRAINAGE WITH REINFORCED CANAL COVER AT MAGSAYSAY ST. IN BRGY POBLACION,SIBULAN | Sibulan, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONST. OF LINE CANAL DRAINAGE WITH REINFORCED CANAL COVER AT CALINGACION ST. IN BRGY POBLACION,SIBULAN | Sibulan, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION OF DRAINAGE CANAL AT DIVINAGRACIA STREET, POBLACION, SIBULAN | Sibulan, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT OF DRAINAGE CANAL, MAGATAS, SIBULAN | Sibulan, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION OF DRAINAGE CANAL WITH COVER(PATHWAY),BARANGAY MOTONG.DUMAGUETE CITY | Dumaguete City, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT OF DRAINAGE CANAL, BARANGAY LOOC, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT OF DRAINAGE CANAL, PUROK TUGAS, BARANGAY PIAPI, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF DRAINAGE CANAL, OSMEÑA STREET, POBLACION, ZAMBOANGUITA | Zamboanguita, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONSTRUCTION OF DRAINAGE CANAL ALONG VILLANUEVA STREET, BARANGAY POBLACION 4, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION OF DRAINAGE CANAL, BARANGAY BANGA, BAYAWAN CITY | Bayawan City, Negros Oriental | 500000 |  |  |  | 0
RES#861-EXTENSION OF IRRIGATION CANAL OF BARANGAY SUMALIRING, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF ROAD, SAMAKA VILLAGE, BARANGAY MABIGO, CANLAON CITY | Canlaon City, Negros Oriental | 2189733 |  |  |  | 0
RES#861-CONCRETING OF BARANGAY ROAD, BAYOG, CANLAON CITY | Canlaon City, Negros Oriental | 500000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF CABARON-QUEZON PROVINCIAL ROAD, VALLEHERMOSO | Vallehermoso, Negros Oriental | 278521 |  |  |  | 0
RES#861-CONCRETING OF ROAD FROM SO. PISOK TO BALAYSUNGAYAN, BRGY POBLACION, GUIHULNGAN | Guihulngan City, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF KASINGAN-TRINIDAD FARM TO MARKET ROAD, GUIHULNGAN CITY | Guihulngan City, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BRGY MAGSAYSAY TO BRGY NAGSAHA, GUIHULNGAN CITY | Guihulngan City, Negros Oriental | 780739 |  |  |  | 0
RES#861-IMPROVEMENT OF BARANGAY ROAD, MALUSAY, GUIHULNGAN CITY | Guihulngan City, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY CALAMBA, GUIHULNGAN CITY | Guihulngan City, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY CALUPAAN, GUIHULNGAN CITY | Guihulngan City, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BRGY BALUGO, GUIHULNGAN CITY | Guihulngan City, Negros Oriental | 500000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF HILAITAN-KASINGAN PROVINCIAL ROAD, GUIHULNGAN CITY | Guihulngan City, Negros Oriental | 600000 |  |  |  | 0
RES#861-CONSTRUCTION & IMPROVEMENT OF SO. PUNONG, TRINIDAD TO SANDAYAO FARM TO MARKET ROAD, GUIHULNGAN CITY | Guihulngan City, Negros Oriental | 3000000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF LA LIBERTAD-PACUAN PROVINCIAL ROAD, LA LIBERTAD | La Libertad, Negros Oriental | 350000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF LA LIBERTAD-SOLONGON PROVINCIAL ROAD, LA LIBERTAD | La Libertad, Negros Oriental | 350000 |  |  |  | 0
RES#861-ROAD CONCRETING, SITIO AMPALALI-SITIO PINAGHUGASAN, BRGY. AYA, LA LIBERTAD | La Libertad, Negros Oriental | 2305772 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY CANLAHAO, JIMALALUD | Jimalalud, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD GOING TO BARANGAY BANOG, JIMALALUD | Jimalalud, Negros Oriental | 627205 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT OF SAMPOBALICAN ROAD, JIMALALUD | Jimalalud, Negros Oriental | 600000 |  |  |  | 0
RES#861-IMPROVEMENT OF AGUTAYON-MAHANLUD-OWACAN ROAD, JIMALALUD | Jimalalud, Negros Oriental | 1000000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF JIMALALUD-BANGCAL PROVINCIAL ROAD, JIMALALUD | Jimalalud, Negros Oriental | 1000000 |  |  |  | 0
RES#861-CONCRETING OF ROAD LEADING TO TAYASAN NATIONAL HIGH SCHOOL, BRGY MATUOG, TAYASAN | Tayasan, Negros Oriental | 300000 |  |  |  | 0
RES#861-REHABILITATION/IMPROVEMENT OF PINALUBNGAN-GUINCALABAN ROAD, TAYASAN | Tayasan, Negros Oriental | 1650000 |  |  |  | 0
RES#861-REHABILITATION/IMPROVEMENT OF MATUOG-CAMBAYE-TAMBULAN ROAD, TAYASAN | Tayasan, Negros Oriental | 1000000 |  |  |  | 0
RES#861-CONCRETING OF CABANO STREET, POBLACION, TAYASAN | Tayasan, Negros Oriental | 1000000 |  |  |  | 0
RES#861-REHABILITATION OF PINDAHAN-TANLAD FARM-TO-MARKET ROAD(FMR), TAYASAN | Tayasan, Negros Oriental | 805778 |  |  |  | 0
RES#861-REHABILITATION/IMPROVEMENT OF NUMNUM FARM-TO-MARKET ROAD(FMR), TAYASAN | Tayasan, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF BARANGAY ROAD, KILABAN, AYUNGON | Ayungon, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF BARANGAY ROAD, INIBAN, AYUNGON | Ayungon, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF BARANGAY ROAD, MAASLUM, AYUNGON | Ayungon, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY MANOGTONG, AYUNGON | Ayungon, Negros Oriental | 500000 |  |  |  | 0
RES#861-REHABILITATION/IMPROVEMENT OF MABATO-CAROL-AN-NABHANG-LAMIGAN-BANBAN PROVINCIAL ROAD, AYUNGON | Ayungon, Negros Oriental | 500000 |  |  |  | 0
RES#861-REHABILITATION/IMPROVEMENT OF CANDANA-AY-ANIBONG-TAMPOCON PROVINCIAL ROAD, AYUNGON | Ayungon, Negros Oriental | 500000 |  |  |  | 0
RES#861-REHABILITATION OF FARM-TO-MARKET ROAD, MAXINO STREET, POBLACION, AYUNGON | Ayungon, Negros Oriental | 1000000 |  |  |  | 0
RES#861-CONCRETING OF BRGY ROAD,LUCAY,MANJUYOD | Manjuyod,Neg.Or. | 1000000 |  |  |  | 0
RES#861-IMPROVEMENT OF KAUSWAGAN BRIDGE(APPROACH), BARANGAY KAUSWAGAN, MANJUYOD | Manjuyod, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY KAUSWAGAN, MANJUYOD | Manjuyod, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF BARANGAY ROAD, SACSAC, MANJUYOD | Manjuyod, Negros Oriental | 476808 |  |  |  | 0
RES#861-CONCRETING OF ROAD, BARANGAY SALVACION, MANJUYOD | Manjuyod, Negros Oriental | 500000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF MANJUYOD-BANTOLINAO PROVINCIAL ROAD, MANJUYOD | Manjuyod, Negros Oriental | 350000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF CAMPUYO PROVINCIAL ROAD, MANJUYOD | Manjuyod, Negros Oriental | 350000 |  |  |  | 0
RES#861-IMPROVEMENT OF FARM-TO-MARKET ROAD, BARANGAY TANGLAD, MANJUYOD | Manjuyod, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONCRETING OF ROAD,BRGY CABUGAN, BINDOY | Bindoy,Neg.Or. | 400000 |  |  |  | 0
RES#861-CONCRETING OF ROAD, BRGY DOMOLOG,BINDOY | Bindoy,Neg.Or. | 400000 |  |  |  | 0
RES#861-CONCRETING & REHABILITATION OF BINDOY-POBLACION ROAD, BINDOY | Bindoy, Negros Oriental | 200000 |  |  |  | 0
RES#861-CONCRETING & REHABILITATION OF BINDOY-MATIABAS-BULOD-ATOTES-NALUNDAN PROVINCIAL ROAD, BINDOY | Bindoy, Negros Oriental | 350000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD GOING TO PANAMBALON AGRICULTURAL FACILITIES, BRGY. PANAMBALON, BAIS CITY | Bais City, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF THE INTERIOR STREETS AT SO. SAN JOSE, BRGY. II, BAIS CITY | Bais City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-ROOFING OF FOOTBRIDGE, BARANGAY I, BAIS CITY | Bais City,Neg.Or. | 500000 |  |  |  | 0
RES#861-CONCRETING OF POBLACION-NORSU RD,MABINAY | Mabinay,Neg.Or. | 1500000 |  |  |  | 0
RES#861-CONSTRUCTION OF HIMOCDONGON FOOTBRIDGE, HIMOCDONGON, MABINAY | Mabinay, Negros Oriental | 2000000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY CANGGOHOB, MABINAY | Mabinay, Negros Oriental | 200000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD,BRGY DAHILE,MABINAY | Mabinay,Neg.Or. | 400000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF PANIABONAN-LUYANG ROAD SECTION, MABINAY | Mabinay, Negros Oriental | 275000 |  |  |  | 0
RES#861-CONCRETING OF FARM-TO-MARKET ROAD, SO. PUNGLO, BARANGAY STO. NIÑO, TANJAY CITY | Tanjay City, Negros Oriental | 2587520 |  |  |  | 0
RES#861-IMPROVEMENT OF BARANGAY ROAD, MANIPIS, TANJAY CITY | Tanjay City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY SAN MIGUEL, TANJAY CITY | Tanjay City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BRGY IV, TANJAY CITY | Tanjay City | 800000 |  |  |  | 0
RES#861-IMPROVEMENT OF PAL-EW-STO. NIÑO ROAD, TANJAY CITY | Tanjay City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BRGY 8,TANJAY CITY | Tanjay City | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY AZAGRA-KANDANGKI ROAD, TANJAY CITY | Tanjay City, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF ROAD FROM STO. NIÑO STREET TO NABULAGAN ACTIVITY CENTER, BARANGAY POBLACION 6, TANJAY CITY | Tanjay City, Negros Oriental | 500000 |  |  |  | 0
RES#861-REPAIR/IMPROVEMENT OF ROMERO BRIDGE, BARANGAY SAN ISIDRO, TANJAY CITY | Tanjay City, Negros Oriental | 600000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY NOVALLAS, TANJAY CITY | Tanjay City, Negros Oriental | 500000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF INAWASAN-ALIIS ROAD, PAL-EW-STO.NIÑO ROAD SECTION, TANJAY CITY | Tanjay City, Negros Oriental | 400000 |  |  |  | 0
RES#861-CONSTRUCTION OF ONE-LANE BRIDGE, POBLACION, PAMPLONA | Pamplona, Negros Oriental | 1000000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY MANGOTO, PAMPLONA | Pamplona, Negros Oriental | 1000000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY STA. AGUEDA, PAMPLONA | Pamplona, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY YUPISAN, PAMPLONA | Pamplona, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF BARANGAY ROAD, MAGSUSUNOG, PAMPLONA | Pamplona, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF BALAYONG-INAWASAN-CALICANAN ROAD, PAMPLONA | Pamplona, Negros Oriental | 3000000 |  |  |  | 0
RES#861-IMPROVEMENT OF BARANGAY ROAD, BARANGAY MALALANGSI, PAMPLONA | Pamplona, Negros Oriental | 1000000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY SAN ISIDRO, PAMPLONA | Pamplona, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY SIMBORIO-MAMBURAO ROAD, PAMPLONA | Pamplona, Negros Oriental | 1000000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD GOING TO MUNICIPAL PUBLIC CEMETERY, BARANGAY MAG-ABO, AMLAN | Amlan, Negros Oriental | 627950 |  |  |  | 0
RES#861-IMPROVEMENT OF SILAB-PANUSUAN ROAD, BARANGAY SILAB, AMLAN | Amlan, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY JANTI-ANON, AMLAN | Amlan, Negros Oriental | 500000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF AMLAN-SILAB PROVINCIAL ROAD, AMLAN | Amlan, Negros Oriental | 300000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF BIO-OS-JANTIANON PROVINCIAL ROAD, AMLAN | Amlan, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONCRETING OF ACCESS ROAD TO RESETTLEMENT SITE, BARANGAY STO. NIÑO, SAN JOSE | San Jose, Negros Oriental | 2000000 |  |  |  | 0
RES#861-CONCRETING OF POBLACION-TAPON NORTE BY-PASS ROAD, SAN JOSE | San Jose, Negros Oriental | 619465 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY CANCAWAS, SAN JOSE | San Jose, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY BASAK, SAN JOSE | San Jose, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY SIAPO, SAN JOSE | San Jose, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY SRA. ASCION, SAN JOSE | San Jose, Negros Oriental | 400000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF TAMPI-SIAPO PROVINCIAL ROAD, SAN JOSE | San Jose, Negros Oriental | 400000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF SRA. ASCION-NAIBA PROVINCIAL ROAD, SAN JOSE | San Jose, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONCRETING OF SAN ANTONIO ST. IN BRGY POBLACION, SIBULAN | Sibulan, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF SAN ANTONIO PROVINCIAL ROAD, SAN ANTONIO, SIBULAN | Sibulan, Negros Oriental | 1000000 |  |  |  | 0
RES#861-CONSTRUCTION OF PATHWAYS ALONG BARANGAY AJONG FISHERIES PROJECT, SIBULAN | Sibulan, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY BOLOCBOLOC, SIBULAN | Sibulan, Negros Oriental | 500000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF BOLOCBOLOC-AGAN-AN PROVINCIAL ROAD, SIBULAN | Sibulan, Negros Oriental | 150000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF SIBULAN-MASLOG PROVINCIAL ROAD, SIBULAN | Sibulan, Negros Oriental | 150000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF SAN ANTONIO-MALINDOG PROVINCIAL ROAD, SIBULAN | Sibulan, Negros Oriental | 150000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF BARANGAY MAGSUSUNOG,PAMPLONA TO ENRIQUE VILLANUEVA ROAD SECTION,SIBULAN | Sibulan, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT PUROK 3, LOWER BATINGUEL, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 600000 |  |  |  | 0
RES#861-CONTINUATION OF ROAD IMPROVEMENT BESIDE CALVARY CHAPEL, BRGY. MOTONG, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 600000 |  |  |  | 0
RES#861-CONCRETING OF ROAD LEADING TO CASA MIANI ARVEDE, BARANGAY TALAY, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 800000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, PUROK MALINAWON, BARANGAY TALAY, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF ROAD JUNCTION HABITAT III GOING TO CARITAS VILLAGE II,BRGY.BAJUMPANDAN,DUMAGUETE CITY | Dumaguete City, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF ROAD JUNCTION OF BAJUMPANDAN-BABAJUBA ROAD, BRGY BAJUMPANDAN,DUMAGUETE CITY | Dumaguete City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-CONTINUATION OF CONCRETING OF STA.MONICA ROAD, BARANGAY BANILAD, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 800000 |  |  |  | 0
RES#861-IMPROVEMENT OF THE INTERIOR ROAD AT BARANGAY MANGNAO, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 800000 |  |  |  | 0
RES#861-IMPROVEMENT OF MANGNAO-BANILAD ROAD LEADING TO CHAPEL, BRGY MANGNAO, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONTINUATION FOR THE CONCRETING OF BABAJUBA ROAD, BARANGAY BAGACAY, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 800000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD & DRAINAGE CANAL,LESANA SUBDIVISION EXTENSION,BRGY, BAGACAY,DUMAGUETE CITY | Dumaguete City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-CONCRETING OF ROAD, BARANGAY JUNOB, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT OF ROAD AT CANDAY-ONG,BRGY. CALINDAGAN, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT OF INTERIOR ROAD, BARANGAY TINAGO, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT OF INTERIOR ROAD, POBLACION BRGY. 2, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONTINUATION OF CONCRETING OF ROAD AT RAYMUND STREET, BARANGAY DARO, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 800000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT VILLA ALEGRE, PUROK 4, BARANGAY BATINGUEL, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF ROAD, BARANGAY CAMANJAC, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 800000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD LEADING TO AMIGO SUBDIVISION, BARANGAY PIAPI, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 708771 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT OF ROAD & DRAINAGE CANAL, BARANGAY BANTAYAN, DGTE. CITY | Dumaguete City, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD & DRAINAGE CANAL LEADING TO SAN VICENTE CHAPEL, BRGY.MANGNAO, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 1300000 |  |  |  | 0
RES#861-CONCRETING OF ROAD ALONG HABITAT I, UPPER UPDD-HOAI HOUSING PROJECT,BAJUMPANDAN, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF ROAD LEADING TO SR. STO. NIÑO CHAPEL, BRGY. CALINDAGAN, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 1000000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD & DRAINAGE CANAL NEAR SILLIMAN GRANDSTAND GOING TO PUBLIC MARKET, BRGY. DARO, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 1300000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT OF ROAD & DRAINAGE CANAL WITH COVER & ROAD SHOULDER,BRGY. JUNOB, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 1300000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF DUMAGUETE-PEO PROVINCIAL ROAD, DUMAGUETE CITY | Dumaguete City, Negros Oriental | 100000 |  |  |  | 0
RES#861-CONCRETING OF VALENCIA-PALINPINON ROAD, VALENCIA | Valencia, Negros Oriental | 2753462 |  |  |  | 0
RES#861-CONCRETING OF ROAD, SAGBANG, VALENCIA | Valencia,Neg.Or. | 500000 |  |  |  | 0
RES#861-CONCRETING OF ROAD, EAST BALABAG, VALENCIA | Valencia, NegOr. | 1000000 |  |  |  | 0
RES#861-ADDITIONAL APPROPRIATION FOR THE CONSTRUCTION OF FOOTBRIDGE, PUROK LUBI, BRGY MALAUNAY, VALENCIA | Valencia, Negros Oriental | 546390 |  |  |  | 0
RES#861-IMPROVEMENT OF MALAUNAY-DOBDOB ROAD, VALENCIA | Valencia, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF ROAD,BRGY BALUGO,VALENCIA | Valencia, NegOr. | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF OGAHONG-PALINPINON ROAD, VALENCIA | Valencia, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY LUNGA, VALENCIA | Valencia, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY APOLOY, VALENCIA | Valencia, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT BARANGAY BONG-AO,VALENCIA GOING TO CANTIL-E ROAD, DUMAGUETE CITY,VALENCIA | Valencia, Negros Oriental | 500000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF VALENCIA-BONGBONG PROVINCIAL ROAD, VALENCIA | Valencia, Negros Oriental | 700000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF VALENCIA-PALINPINON PROVINCIAL ROAD, VALENCIA | Valencia, Negros Oriental | 200000 |  |  |  | 0
RES#861-CONCRETING OF PROVINCIAL ROAD FROM TUBOD TO BARANGAY TIMBAO, BACONG | Bacong, Negros Oriental | 2000000 |  |  |  | 0
RES#861-REPAIR OF FOOTBRIDGE IN UPPER ISUGAN, BARANGAY ISUGAN, BACONG | Bacong, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY SULODPAN, BACONG | Bacong, Negros Oriental | 617438 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF BACONG-TIMBAO PROVINCIAL ROAD, BACONG | Bacong, Negros Oriental | 450000 |  |  |  | 0
RES#861-ROAD CONCRETING PROJECT AT MAAYONGTUBIG, DAUIN | Dauin, Negros Oriental | 1000000 |  |  |  | 0
RES#861-ROAD CONCRETING PROJECT AT MALONGCAY DACU, DAUIN | Dauin, Negros Oriental | 1500000 |  |  |  | 0
RES#861-ADDITIONAL APPROPRIATION FOR THE ROAD IMPROVEMENT OF CAPITAN PONSO EXTENSION,BRGY.POBLACION-DIST.II,DAUIN | Dauin, Negros Oriental | 900000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF MASAPLOD-BASLAY PROVINCIAL ROAD, DAUIN | Dauin, Negros Oriental | 350000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY BASAK-NASIG-ID, ZAMBOANGUITA | Zamboanguita, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT/REHABILITATION OF ROAD AT. SO.BUTO TO SO.MANGGA,BRGY.MAYABON,ZAMBOANGUITA | Zamboanguita, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF LUMANG-E ROAD, BARANGAY MALUAY, ZAMBOANGUITA | Zamboanguita, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD ALONG POBLACION-CALANGO ROAD, ZAMBOANGUITA | Zamboanguita, Negros Oriental | 401752 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD FROM JUNCTION NATIONAL HIGHWAY TO BRGY LUTUBAN ROAD,ZAMBOANGUITA | Zamboanguita, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF MAG-ABO-NABAGO ROAD, BARANGAY MALUAY, ZAMBOANGUITA | Zamboanguita, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONCRETING OF CROSSING NATIONAL HIGHWAY-UPPER PANLIGUIRAN FARM-TO-MARKET ROAD, SIATON | Siaton, Negros Oriental | 2831850 |  |  |  | 0
RES#861-IMPROVEMENT OF BONAWON-CALANGAG ROAD, SIATON | Siaton, Negros Oriental | 2821429 |  |  |  | 0
RES#861-IMPROVEMENT OF PANLIGUIRAN-BALINGASAG ROAD, BARANGAY MANTUYOP, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF BARANGAY ROAD AT PROPER MANTIQUIL, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF BARANGAY ROAD GOING UP TO SITIO JUMALON, SALAG, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF ROAD AT PUROK 2, BARANGAY CANAWAY, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF BARANGAY ROAD FROM INALAD TO CAMBOAY ROAD, SIATON | Siaton, Negros Oriental | 250000 |  |  |  | 0
RES#861-CONCRETING OF BARANGAY ROAD, BARANGAY MALOH, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF PORTION OF THE BARANGAY ROAD, BARANGAY DATAG, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF ROAD, BRGY SAN JOSE, SIATON | Siaton, Neg.Or. | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF BARANGAY ROAD, BARANGAY ALBIGA, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF CANDUGAY ROAD FROM JUNCTION TO BRGY. HALL, BRGY POBLACION IV, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONCRETING OF ROAD, BONBONON, SIATON | Siaton, Neg.Or. | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF VARIOUS ROADS/STREET OF BARANGAY POBLACION 1, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BRGY APOLOY, SIATON | Siaton, Neg.Or. | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF BARANGAY ROAD, SAN MIGUEL, STA. CATALINA | Sta. Catalina, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD AT. SO. APUYA, BARANGAY MANALONGON, STA. CATALINA | Sta. Catalina, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD FROM BRGY PROPER OF MILAGROSA GOING TO STATION OF THE CROSS AT SO. BALANGA,MILAGROSA, STA.CATALINA | Sta. Catalina, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONCRETING OF FARM TO MARKET ROAD, BARANGAY MABUHAY, STA. CATALINA | Sta. Catalina, Negros Oriental | 300000 |  |  |  | 0
RES#861-REHABILITATION/IMPROVEMENT OF ROAD FROM PROPER MANSAGOMAYON HIGHWAY GOING TO TALOSTOS FALLS, BRGY. MANSAGOMAYON,STA. CATALINA | Sta. Catalina, Negros Oriental | 100000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD FROM NATIONAL HIGHWAY TO SO.MAMPAS,BRGY NAGBALAYE,STA.CATALINA | Sta. Catalina, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY NAGBINLOD, STA. CATALINA | Sta. Catalina, Negros Oriental | 600000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF ALANGILAN-MATANOG PROVINCIAL ROAD, STA. CATALINA | Sta. Catalina, Negros Oriental | 500000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF BUNSOD-AMIO PROVINCIAL ROAD, STA. CATALINA | Sta. Catalina, Negros Oriental | 500000 |  |  |  | 0
RES#861-REHABILITATION OF THE FRIENDSHIP HIGHWAY, VILLASOL-MANDUAO ROAD SECTION, BAYAWAN | Bayawan City, Negros Oriental | 2920851 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY CANSUMALIG-SAN ISIDRO, BAYAWAN CITY | Bayawan City, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD IN SO. CAN-ASAM, BARANGAY SAN MIGUEL, BAYAWAN CITY | Bayawan City, Negros Oriental | 250000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY VILLASOL, BAYAWAN CITY | Bayawan City, Negros Oriental | 250000 |  |  |  | 0
RES#861-REHAB. & IMPROVEMENT OF MALABUGAS-SAN ROQUE-MINABA-TAYAWAN-KALUMBOYAN-TABUAN-ALI-IS PROVINCIAL ROAD,BAYAWAN | Bayawan City, Negros Oriental | 575000 |  |  |  | 0
RES#861-REHABILITATION & IMPROVEMENT OF TABUAN-BANAYBANAY PROVINCIAL ROAD,BAYAWAN | Bayawan City, Negros Oriental | 400000 |  |  |  | 0
RES#861-CONCRETING OF TIABANAN-CRUSHER BARANGAY ROAD, BAL-OS, BASAY | Basay, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONCRETING OF CABONGBONGAN-SANDIG ROAD, BONGALONAN, BASAY | Basay, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONCRETING OF SO. BIGA-A JUNCTION ROAD TO PROPER OLANDAO, BASAY | Basay, Negros Oriental | 500000 |  |  |  | 0
RES#861-ADDITONAL APPROPRIATION FOR THE CONCRETING OF ROAD LEADING TO BAL-OS NATIONAL HIGH SCHOOL,BAL-OS,BASAY | Basay, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF ROAD, BARANGAY MAGLINAO-BARANGAY CABATUANAN, BASAY | Basay, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF DARO-LINANTAYAN BARANGAY ROAD, BASAY | Basay, Negros Oriental | 546299 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY LINOTHANGAN, CANLAON CITY | Canlaon City, Negros Oriental | 333706 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY BULADO, GUIHULNGAN | Guihulngan City, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY TACPAO, GUIHULNGAN | Guihulngan City, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY NASUNGGAN, LA LIBERTAD | La Libertad, Negros Oriental | 217009 |  |  |  | 0
RES#861-CONSTRUCTION OF WATERWORKS SYSTEM, BARANGAY OWACAN, JIMALALUD | Jimalalud, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY ELI, JIMALALUD | Jimalalud, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY TAMBO, AYUNGON | Ayungon, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATER SYSTEM, BARANGAY POBLACION, MANJUYOD | Manjuyod, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATER SYSTEM, BARANGAY SUNDO-AN, MANJUYOD | Manjuyod, Negros Oriental | 200000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATER SYSTEM, SITIO PALAHAN, BRGY. MAASLUM, MANJUYOD | Manjuyod, Negros Oriental | 200000 |  |  |  | 0
RES#861-CONCTRUCTION OF WATERWORKS SYSTEM, BARANGAY TINAOGAN, BINDOY | Bindoy, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY PANGALAYCAYAN, BINDOY | Bindoy, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY MANSEJE, BINDOY | Bindoy, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT OF DEEPWELLS, BARANGAY CAMBAGAHAN, BAIS CITY | Bais City, Negros Oriental | 100000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY OLD NAMANGKA, MABINAY | Mabinay, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY INAPOY, MABINAY | Mabinay, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY LAMDAS, MABINAY | Mabinay, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY TARA, MABINAY | Mabinay, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY BAHI-AN, TANJAY CITY | Tanjay City, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BASAK, SAN JOSE | San Jose, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM IN BARANGAY JILOCON, SAN JOSE | San Jose, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONSTRUCTION OF WATERWORKS SYSTEM, BARANGAY SAN ROQUE, SAN JOSE | San Jose, Negros Oriental | 200000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM, BARANGAY TAPON NORTE, SAN JOSE | San Jose, Negros Oriental | 200000 |  |  |  | 0
RES#861-INSTALLATION OF WATERWORKS SYSTEM, SO.TUBOD & SO. MAG-ELABI, BRGY. ENRIQUE VILLANUEVA, SIBULAN | Sibulan, Negros Oriental | 700000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM FROM BRGY. BATUHON DACU LEADING TO CASILE E/S,BRGY.BATUHON DACU,DAUIN | Dauin, Negros Oriental | 300000 |  |  |  | 0
RES#861-EXPANSION OF WATER SYSTEM, BARANGAY SANDULOT, SIATON | Siaton, Negros Oriental | 200000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM AT BRGY. CASALA-AN, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATER SYSTEM., BARANGAY BONAWON, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-ADDITIONAL APPROPRIATION OF WATER SYSTEM, BARANGAY MALOH, SIATON | Siaton, Negros Oriental | 100000 |  |  |  | 0
RES#861-CONST. OF WATERWORKS SYSTEM IN SO.LOWER NATO OF STO.NIÑO,TANJAY TO SO.UPPER NATO OF BRGY. ALI-IS,BAYAWAN,ALI-IS,BAYAWAN | Bayawan City, Negros Oriental | 500000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM IN BARANGAY BANAYBANAY,BAYAWAN CITY | Bayawan City, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF WATERWORKS SYSTEM IN SO. MALUBAG,BARANGAY SAN ISIDRO, BAYAWAN CITY | Bayawan City, Negros Oriental | 300000 |  |  |  | 0
RES#861-ADDITIONAL APPROPRIATION FOR THE CONSTRUCTION OF RIVER DIKE,BRGY BAGTIC,MABINAY | Mabinay, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION OF DIKE ALONG BANICA RIVER SPECIFICALLY AT PUROK NARRA AREA, CADAWINONAN,DUMAGUETE CITY | Dumaguete City, Negros Oriental | 1000000 | 2015-06-16 | 2015-08-31 |  | 3030 |  | on -going
RES#861-CONTINUATION & IMPROVEMENT OF EXISTING DIKE, BARANGAY MALABUHAN, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION OF FLOOD CONTROL DIKE, BARANGAY STO. ROSARIO, STA. CATALINA | Sta. Catalina, Negros Oriental | 1000000 |  |  |  | 0
RES#861-CONSTRUCTION OF ALIS BOX CULVERT, POBLACION, BASAY | Basay, Negros Oriental | 650000 |  |  |  | 0
RES#861-REHABILITATION OF DRAINAGE SYSTEM IN FRONT OF JANTIANON NATIONAL HIGH SCHOOL,BRGY.JANTIANON, AMLAN | Amlan, Negros Oriental | 40000 |  |  |  | 0
RES#861-CONSTRUCTION/REHAB/IMPROVEMENT OF DRAINAGE CANAL AT PROPER PULANGBATO, VALENCIA | Valencia, Negros Oriental | 100000 |  |  |  | 0
RES#861-CONSTRUCTION/REHABILITATION OF DRAINAGE CANAL SYSTEM IN BRGY. PULANGBATO, VALENCIA | Valencia, Negros Oriental | 20000 |  |  |  | 0
RES#861-ROAD CONCRETING IN BRGY.MANIPIS,TANJAY CITY | Tanjay City | 500000 |  |  |  | 0
RES#861-ROAD CONCRETING IN BRGY.PANAMANGAN,BAIS | Bais City,Neg.Or. | 500000 |  |  |  | 0
RES#861-ROAD CONCRETING IN BRGY. TUGAS, TANJAY CITY | Tanjay City | 500000 |  |  |  | 0
RES#861-REHABILITATION OF LOCAL ROADS FROM YMALAY APARTMENT GOING TO NORTH MAHINABANGON,CAMANJAC,DGTE.CITY | Dumaguete City, Negros Oriental | 100000 |  |  |  | 0
RES#861-CONSTRUCTION OF LOCAL ROADS CONNECTING BRGY.LIPTONG,BACONG & BRGY. LIPTONG, VALENCIA | Valencia, Negros Oriental | 250000 |  |  |  | 0
RES#861-CONSTRUCTION OF COMMUNAL SPRING BOX IN BRGY. BUCAD, BAYAWAN CITY | Bayawan City, Negros Oriental | 50000 |  |  |  | 0
RES#861-CONSTRUCTION OF COMMUNAL SPRING BOX IN SO. UPPER TIGBAYAWAN,TAYAWAN,BAYAWAN | Bayawan City, Negros Oriental | 50000 |  |  |  | 0
RES#861-REHABILITATION OF LOCAL GOVERNMENT-OWNED POTABLE WATER SUPPLY SYSTEMS IN BRGY. DAHILE,MABINAY | Mabinay, Negros Oriental | 70000 |  |  |  | 0
RES#861-CONSTRUCTION/REHAB OF POTABLE WATER SYSTEM, BRGY. MANALONGON, STA. CATALINA | Sta. Catalina, Negros Oriental | 20000 |  |  |  | 0
RES#861-CONSTRUCTION/REHAB OF POTABLE WATER SYSTEM, BRGY. BANAYBANAY, BAYAWAN CITY | Bayawan City, Negros Oriental | 20000 |  |  |  | 0
RES#861-CONSTRUCTION/REHAB OF POTABLE WATER SYSTEM, BRGY. KALAMTUKAN, BAYAWAN CITY | Bayawan City, Negros Oriental | 20000 |  |  |  | 0
RES#861-CONSTRUCTION/REHAB OF POTABLE WATER SYSTEM, BRGY. LAPAY, BAYAWAN CITY | Bayawan City, Negros Oriental | 20000 |  |  |  | 0
RES#861-CONSTRUCTION/REHAB OF POTABLE WATER SYSTEM, BRGY. VILLASOL, BAYAWAN CITY | Bayawan City, Negros Oriental | 20000 |  |  |  | 0
RES#861-CONSTRUCTION OF COMFORT ROOM IN BRGY. OWACAN, JIMALALUD | Jimalalud, Negros Oriental | 100000 |  |  |  | 0
RES#861-CONSTRUCTION OF COMFORT ROOM IN BRGY. LUZ, GUIHULNGAN | Guihulngan City, Negros Oriental | 100000 |  |  |  | 0
RES#861-CONSTRUCTION/REHABILITATION/IMPROVEMENT OF BIO-OS, AMLAN WATER WORKS SYSTEM | Amlan, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION/REHABILITATION/IMPROVEMENT OF JANTIANON, AMLAN WATER WORKS SYSTEM | Amlan, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT/REHABILITATION/ OF TIGUIB, AYUNGON WATER WORKS SYSTEM | Ayungon, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT OF CONCRETE ROAD FROM ELEM SCHOOL TO PROV'L RD. OF BRGY CAROL-AN,AYUNGON | Ayungon, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION//REHABILITATION/IMPROVEMENT OF DAWIS, BAYAWAN WATER WORKS SYSTEM | Bayawan City, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION OF WATER WORKS SYSTEM OF TINAOGAN, BINDOY TO MANTALIP REEF | Bindoy, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONSTRUCTION/REHABILITATION OF DAUIN WATER WORKS SYSTEM | Dauin, Negros Oriental | 450000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT/REHABILITATION/ OF BAKID, GUIHULNGAN WATER WORKS SYSTEM | Guihulngan City, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT/REHABILITATION/ OF PLAGATASANON, GUIHULNGAN WATER WORKS SYSTEM | Guihulngan City, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION//REHABILITATION/IMPROVEMENT OF MAMBAID, JIMALALUD WATER WORKS SYSTEM | Jimalalud, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION//REHABILITATION/IMPROVEMENT OF POLOPANTAO, JIMALALUD WATER WORKS SYSTEM | Jimalalud, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION//REHABILITATION/IMPROVEMENT OF BAE, JIMALALUD WATER WORKS SYSTEM | Jimalalud, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION//REHABILITATION OF BRGY. TUPAS CANAL/DRAINAGE SYSTEM | Manjuyod, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONSTRUCTION//REHABILITATION OF JANAYJANAY, SAN JOSE WATER WORKS SYSTEM | San Jose, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION//REHABILITATION OF CASALAAN, SIATON WATER WORKS SYSTEM | Siaton, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION/REHABILITATION OF TALALAK, SIATON WATER WORKS SYSTEM | Siaton, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT/REHABILITATION OF MALUSAY, GUIHULNGAN WATER WORKS SYSTEM | Guihulngan City, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT/REHABILITATION OF SAN JOSE, STA. CATALINA WATER WORKS SYSTEM | Sta. Catalina, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT/REHABILITATION OF SAN MIGUEL, STA. CATALINA WATER WORKS SYSTEM | Sta. Catalina, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION/IMPROVEMENT/REHABILITATION OF TALALAK, STA. CATALINA WATER WORKS SYSTEM | Sta. Catalina, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION/REHABILITATION OF DRAINAGE SYSTEM, EAST BALABAG, VALENCIA | Valencia, Negros Oriental | 150000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE PAVEMENT, BARANGAY MALAIBA, CANLAON CITY | Canlaon City, Negros Oriental | 300000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE PAVEMENT, BARANGAY BUENAVISTA, GUIHULNGAN CITY | Guihulngan City, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE PAVEMENT, SO. MALANGSA, BARANGAY LAMOGONG,MANJUYOD | Manjuyod, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE PAVEMENT, SO. PROPER, BARANGAY BULOD, BINDOY | Bindoy, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE PAVEMENT, BARANGAY PIÑAHAN, BINDOY | Bindoy, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE PAVEMENT, BARANGAY PANIABONAN, MABINAY | Mabinay, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION OF MPP, BARANGAY DAGBASAN, MABINAY | Mabinay, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE PAVEMENT & DRAINAGE CANAL,HABITAT 4,BARANGAY BAJUMPANDAN,DUMAGUETE CITY | Dumaguete City, Negros Oriental | 400000 |  |  |  | 0
RES#861-IMPROVEMENT OF MULTI-PURPOSE PAVEMENT, SITIO NASIPIT, CABANGAHAN, SIATON | Siaton, Negros Oriental | 500000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE PAVEMENT AT SO. BAISAN, KALUMBOYAN, BAYAWAN CITY | Bayawan City, Negros Oriental | 300000 |  |  |  | 0
RES#861-CONSTRUCTION OF MULTI-PURPOSE PAVEMENT, SO. MANGUPO,BARANGAY TAYAWAN, BAYAWAN | Bayawan City, Negros Oriental | 300000 |  |  |  | 0
RES#861-PURCHASE OF ONE(1)UNIT BRAND NEW HYDRAULIC EXCAVATOR(BACKHOE)FOR USE IN THE REPAIR,REHAB OF BRGY ROADS IN THE MUN. OF VALLEHERMOSO | Vallehermoso, Negros Oriental | 5000000 |  |  |  | 0
RES#861-PURCH OF 2-UNITS MINI-DUMPTRUCKS, SIBULAN | Sibulan,Neg.Or. | 1330100 |  |  |  | 0
RES#861-PURCHASE OF MINI-DUMP TRUCK FOR BARANGAY TUBIGON, SIBULAN | Sibulan, Negros Oriental | 800000 |  |  |  | 0
RES#861-PURCHASE OF 1UNIT SKW COBRA 6-WHEELERS DUMP TRUCK & 1 UNIT 4X4 1W DROP SIDE CARGO TRUCK,ZAMBOANGUITA | Zamboanguita, Negros Oriental | 2265480 |  |  |  | 0
RES#861-PURCHASE OF TWO(2)UNITS BRAND NEW BULLDOZER(3-4M3CAP)OF THE PROVINCIAL GOVERNMENT | Dumaguete City, Negros Oriental | 17000000 |  |  |  | 0
RES#861-PURCHASE OF BRAND NEW PAYLOADER(1.7-2.0M3CAP) OF THE PROVINCIAL GOVERNMENT | Dumaguete City, Negros Oriental | 7500000 |  |  |  | 0
RES#861-PURCHASE OF BRAND NEW ROAD ROLLER(10TONS CAP) OF THE PROVINCIAL GOVERNMENT | Dumaguete City, Negros Oriental | 8300000 |  |  |  | 0
RES#861-PURCHASE OF BRAND NEW 6 WHEELER DUMPTRUCKS(10TONS OR 7-8M3 PAYLOAD CAPACITY) | Dumaguete City, Negros Oriental | 17200000 |  |  |  | 0
RES#861-CONSTRUCTION/REHAB OF MULTI-PURPOSE PAVEMENT OF CAMBUCAD BRGY ROAAD GOING TO BALILI,VALENCIA | Valencia, Negros Oriental | 100000 |  |  |  | 0
RES#861-IMPROVEMENT/REHAB. OF MULTI-PURPOSE PAVEMENT IN BRGY KALAMTUKAN, BAYAWAN CITY | Bayawan City, Negros Oriental | 50000 |  |  |  | 0
RES#861-DBP CONVENTION CENTER LOAN AMORTIZATION |  | 7672913 |  |  |  | 1948367.24 |  | Ist Qtr Amortization
RES#861-DILG-THIRD ROAD IMPROVEMENT PROJECT(TRIP) LOAN AMORTIZATION(PC) |  | 103516 |  |  |  | 0
RES#861-DILG-THIRD ROAD IMPROVEMENT PROJECT(TRIP) EQUIPMENT PACKAGE LOAN AMORTIZATION |  | 808310 |  |  |  | 0
RES#861-DBP-CENTRAL BLOCK BUILDING(AT NOPH) LOAN AMORTIZATION |  | 7406231 |  |  |  | 988508.54 |  | Ist Qtr Amortization
Sub-total |  | 296210371 |  |  |  | 2939905.78
ENVIRONMENTAL MANAGEMENT
RES#861-CONSTRUCTION OF CELL TYPE DISPOSAL FACILITY FOR RESIDUALS IN THE MUN. OF BINDOY(PHASE1) | Bindoy, Negros Oriental | 1215326 |  |  |  | 0
RES#861-PURCHASE OF A 6-WHEELER GARBAGE COMPACTOR(4-5 TONS) FOR THE MUN. OF BINDOY | Bindoy, Negros Oriental | 1050000 |  |  |  | 0
Sub-total |  | 2265326 |  |  |  | 0
Grand Total |  | 298475697 |  |  |  | 2939905.78
We hereby certify that we have reviewed the contents and hereby attest to the veracity
and correctness of the data or information contained in this document.
TEODORICO G. REYES | [5 empty] | ROEL R. DEGAMO
Provincial Accountant | [5 empty] | Governor